Stage 2 - Selection of Accelerated Bridge Construction Projects

Appropriately selected ABC alternatives can substantially reduce construction time, impacts to users, and improve safety. Alternatives should be considered very early in the scoping process (concurrent with the Bridge Scoping Worksheet) to allow for potential adjustments in letting date, project schedule, funding, design duration, and time needed for pre-fabrication of bridge elements.

This tool should be used during the scoping process to determine whether the following bridge related issues are present or should be considered during project development. The more questions that have “Yes” or “Possibly” as answers, the more likely that accelerated bridge construction (ABC) techniques may provide a viable solution.

This tool should be filled out and recorded by the District Project Manager, with assistance from the District Bridge Engineer, Traffic Engineer, Resident Engineer, and the Bridge Preliminary Plans Unit and Regional Bridge Construction Engineer.

Refer to pages 3-6 of this document for additional instructions and guidance.

Prepared By:      				Date:                		District:

Additional Assistance Provided By:

Project Information:

| Bridge No.: | TH: | Let Date: | ADT On: ADT Under: |
| --- | --- | --- | --- |
| Project Description (work type, major roadway work also required?, anticipated duration): |  |  |  |

| Question/Issue |  | Yes | No | Poss | N/A | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| - Is it likely that this project will include complex traffic control schemes, long detours, or significant user impacts due to bridge construction? |  |  |  |  |  |  |
| - Is it likely that this project will have an extended duration (more than one construction season, or extend into late fall) due to bridge construction? |  |  |  |  |  |  |
| - Is bridge construction on the critical path of this project? |  |  |  |  |  |  |
| - Are there any issues regarding construction timeframes (e.g. fish spawning, bird nesting, high water, permits, major events)? |  |  |  |  |  |  |
| - Are there critical features or services on the route that need to be considered (e.g. hospital, emergency services, transit, school buses)? |  |  |  |  |  |  |
| - Could additional width be needed on culverts, bridges, or shoulders to maintain traffic on the existing route or the detour route? |  |  |  |  |  |  |
| - Does the existing bridge have features that make it difficult to accommodate staging (truss bridge, slab span, beam spacing issues, etc.)? |  |  |  |  |  |  |
| - Is it likely that temporary bridge structures will be needed? |  |  |  |  |  |  |
| - Could there be a need to maintain railroad traffic? |  |  |  |  |  |  |
| - Might temporary traffic signals be required? |  |  |  |  |  |  |
| - Does it appear that maintenance of traffic will require additional right-of-way? |  |  |  |  |  |  |
| - Will/Can traffic be detoured? If yes: |  |  |  |  |  |  |
|  | - Will the detour route have a detrimental impact on emergency vehicles, school buses, or other sensitive traffic? |  |  |  |  |  |
|  | - Is the local alternate detour route in questionable condition? |  |  |  |  |  |
|  | - Are there load limit restrictions on the detour? |  |  |  |  |  |
|  | - Are there bridge width or height restrictions on the detour? |  |  |  |  |  |
|  | - Are there issues regarding suitability of detour route (length, speed limit, travel time, etc.)? |  |  |  |  |  |
|  | - Are modifications needed at intersections on detour/alternate routes? |  |  |  |  |  |
| - Are there geotechnical (poor soils, contaminated material, etc.) or utility issues that may affect construction? |  |  |  |  |  |  |
| - Could construction impact businesses? |  |  |  |  |  |  |
| - Are there significant risks or other factors (site complexity) that could be mitigated by accelerating bridge construction? |  |  |  |  |  |  |

Additional Considerations:

In addition to the issues listed above, consideration should also be given to staging construction ½ at-a-time, “packaging” additional bridges in the vicinity, and acknowledgment of other planned construction work in the area.  Also, alternative contracting methods such as design build, CMGC, incentive/disincentive, A+B, etc., or traffic control alternatives such as lane rental should be considered in mitigating traffic impacts.

Conclusion:

Based on the findings & conclusions above, further consideration of accelerated bridge construction is warranted: YES NO Project Manager Name: ________________________________ Date: __________ Comments: **Please send a copy of pages 1 & 2 of this completed form to the Bridge Preliminary Plans Unit at MS 610**

If further consideration is warranted the Project Manager should contact the Bridge Office Preliminary Plans Unit and the Regional Bridge Construction Engineer for assistance in selecting appropriate ABC alternatives and techniques.

Stage 2 - Selection of Accelerated Bridge Construction Projects

General Information and Background

The stage 2 ABC selection process has been developed to help bridge owners select project sites that are best suited to use accelerated bridge construction techniques. Specifically, it provides a consistent, objective, and defensible method of selecting appropriate ABC projects.

The stage 2 process should be conducted during the scoping phase to determine which bridge related issues should be considered during project development. Early identification is critical, as it allows those involved with the project to complete the second stage ABC review and begin to identify potential ABC techniques and solutions. A longer-than-normal lead time may be necessary for ABC projects, due to the need to research and develop construction details and design processes. The more questions that are answered with “Yes” or “Possibly”, the more likely that accelerated bridge construction techniques may provide a viable solution. The second stage analysis also identifies which specific ABC techniques and/or alternative contracting methods should be considered.

Instructions

Line By Line Instructions:

Prepared By:, Additional Assistance Provided By:

It is intended that this tool be filled out and recorded by the District Project Manager, with assistance from the District Bridge Engineer, Traffic Engineer, Resident Engineer, and the Bridge Pre-Design and Regional Bridge Construction Engineer from the Bridge Office.

Project Information: (Bridge No., TH, Letting Date, ADT)

Record the basic bridge data, including the ADT on and under the bridge, which may help in determining appropriate staging, traffic control, and ABC alternatives. All of this data (other than letting date) is on the Bridge Inventory Sheet, available from the Bridge Office Data Management Unit, on IHUB at http://webreports3/bridge/Content.aspx

Project Description:

List the major work type such as “bridge replacement”, “bridge redeck with widening”, “superstructure replacement”, etc.  If known, include the approximate duration of the bridge work such as “multiple construction seasons”, “3-4 months”, etc.  If the project includes major roadway work indicate that also, or if the complete focus of the project is bridge construction indicate that it is a “bridge only” project.

Question/Issue No. 1:

Is it likely that this project will include complex traffic control schemes, long detours, or significant user impacts due to bridge construction?

Long detours and complex traffic control schemes may lead to higher construction and roadway user costs, which may make spending additional funds on ABC techniques a cost effective solution.  The more complex the traffic control scheme or the longer the detour route, the more likely ABC can be a viable alternative. Review the possible traffic staging options and detour routes with the District Traffic Engineer to determine the user impacts.

Question/Issue No. 2:

Is it likely that this project will have an extended duration (more than one construction season, or extend into late fall) due to bridge construction?

The Resident Engineer and Regional Bridge Construction Engineer can provide assistance in determining project duration.

ABC alternatives such as a lateral slide, use of precast components, self-propelled modular transporters (SPMT’s), and contracting alternatives such as design build and A+B can reduce the duration of construction activities and roadway user impacts.  The use of prefabricated components can also extend the construction window later into the fall.

Question/Issue No. 3:

Is bridge construction on the critical path of this project?

Question/Issue No. 3 (cont’d):

In assessing the need for accelerated bridge construction it’s important to understand what role bridge construction plays in the overall scope and duration of the project.  If the bridge work is not on the critical path it may not be cost effective to accelerate the bridge portion of the work.

In the early phase of project scoping it may be difficult to answer this question, but discussions with the Resident Engineer and Regional Bridge Construction Engineer should provide enough insight for the purposes of this analysis.

Question/Issue No.4:

Are there any issues regarding construction timeframes (e.g. fish spawning, bird nesting, high water, permits, major events)?

Work with environmental, hydraulics, and DNR representatives to determine if the aforementioned issues may restrict the ability to use conventional construction methods or timeframes, which may lead to compressed construction schedules or reduced access to adjacent right-of-way.  The use of prefabricated components or innovative contracting alternatives may also address this issue. The Resident Engineer, Regional Bridge Construction Engineer, of the Office of Construction and Innovative Contracting can provide assistance in determining viable alternatives and solutions.

Question/Issue No. 5:

Are there critical features or services on the route that need to be considered (e.g. hospital, emergency services, transit, school buses)?

The need to maintain access for emergency services, school buses, transit, etc., can impact project scheduling, duration and staging alternatives. List the known critical services or features that must be considered and whether or not they can be accommodated using conventional construction methods and staging.

Question/Issue No.6:

Could additional width be needed on culverts, bridges, or shoulders to maintain traffic?

Work with the District Bridge and Traffic Engineers to determine if the proposed work will require temporary or permanent widening of other bridges or culverts within the project limits.  If it becomes necessary to spend funds to temporarily widen existing roadways or structures, it may make sense to spend those funds on ABC alternatives, which may also reduce roadway user impacts and construction duration.

Question/Issue No. 7:

Does the existing bridge have features that make it difficult to accommodate staging (truss bridge, slab span, beam spacing issues, etc.)?

Features such as existing beam spacing (i.e. not having a beam along the centerline of the roadway) may limit the ability to use ½ at-a-time construction or other staging alternatives.  Some bridge types, such as trusses are not amenable to widening. Work with the District Bridge Engineer, Regional Bridge Construction Engineer or staff from the Bridge Office Pre-Design Unit to review the existing bridge and proposed work type to identify features that may impact the options for construction staging.

Question/Issue No. 8:

Could temporary bridge structures be required?

If early analysis indicates that ½ at-a-time construction staging, detours, or other fairly simple staging alternatives are not suitable, it may be necessary to construct a temporary bridge. Since temporary structures may cost as much as 60% of the cost of a new bridge, it may make sense to spend some additional funds on ABC alternatives, which may also reduce roadway user impacts and construction duration. Work with the District Bridge, Traffic, Resident, and Regional Bridge Construction Engineer to determine if temporary structures will be needed.

Question/Issue No. 9:

Could there be a need to maintain railroad traffic?

If railroad traffic is carried on or under the bridge, work with the Railroad Administration Section of the Office of Freight and Commercial Vehicle Operations, or the railroad owner to determine what, if any detours or railroad scheduling alternatives are available.  The cost of flagging operations and temporary structures can be significant, so it may make sense to investigate ABC alternatives, which may reduce roadway user and railroad impacts as well as construction duration.

Question/Issue No. 10:

Might temporary traffic signals be required?

This question addresses the same issue as questions 6 and 8, but is related to the cost and impact of using temporary traffic signals or traffic control systems. Work with the District Traffic Engineer to answer this question.

Question/Issue No. 11:

Does it appear that maintenance of traffic will require additional right-of-way?

Same considerations as question No. 10, but related to possible right-of-way acquisition.

Question/Issue No. 12:

Will/Can traffic be detoured?

If it’s already been determined that traffic cannot or will not be detoured, it is not necessary to complete the remainder of question 12, otherwise proceed to the following sub-questions:

12a. Will the detour route have a detrimental impact on emergency vehicles, school buses, or other sensitive traffic?

Similar to question No. 5, but in regards to the proposed detour route.

12b. Is the local alternate detour route in questionable condition?

Work with the District Materials and Traffic Engineers to determine if the available detour routes are in suitable condition or if significant funds would be required to repair or restore the route.

12c. Are there load limit restrictions on the detour?

Work with the District Bridge and Materials Engineers to determine if the proposed work will require temporary load postings or strengthening of bridges, culverts, or roadways within the project limits.  If it becomes necessary to spend funds to strengthen bridges and roadways, it may make sense to spend those funds on ABC alternatives.

12d. Are there bridge width or height restrictions on the detour?

Similar to question 12c, existing bridge height and width restrictions may limit the available detour routes. The District Bridge Engineer should have all of the pertinent information.

12e. Are there other issues regarding the suitability of the detour route (length, speed limit, travel time, etc.)?

List the additional characteristics of the available detour routes that they may make them undesirable. Long detours, routes with reduced speed and increased travel time may result in further consideration of other construction or contract administration alternatives that eliminate or limit the need for a detour.

12f. Are modifications needed at intersections on detour/alternate routes?

Consider the need for temporary signals or signing or modifications that may be needed to existing intersections to accommodate traffic on the detour route.

Question/Issue No.13:

Are there geotechnical (poor soils, contaminated material, etc.) or utility issues that may affect construction?

Review the project limits for geotechnical or utility issues that may affect the timing or cost of the project.   This could include both underground and overhead utilities. The cost of utility relocation or poor soil mitigation can be significant and may be avoided through the use of construction staging or ABC techniques that don’t disturb the affected areas.

Question/Issue No. 14:

Could construction impact businesses?

Similar to question 13, the cost of mitigating impacts to local businesses can be substantial. Staging alternatives ranging from full closure to ½ at-a-time, or even night time construction may help moderate these concerns.  Incentive/disincentive and other contract administration methods may also be good alternatives. List the potential business impacts.

Question/Issue No.15:

Are there significant risks or other factors (site complexity) that could be mitigated by accelerating bridge construction?

List any other known risks or concerns that are not included in any of the previous questions.  Examples might include lack of available concrete production facilities in the region, spring flooding or rapid changes in water elevation or velocity,

Question/Issue No. 15 (cont’d):

limited construction window due to local ordinances, adjacent to vibration sensitive structures, etc.  The District Bridge Engineer or Regional Bridge Construction Engineer may also be able to provide insight regarding this issue.

Additional Considerations:

Before making a final decision as to whether or not accelerated bridge construction is a viable alternative, consideration show also be given to “packaging” additional bridges in the vicinity, and acknowledgment of other planned construction work in the area.  Representatives from the Office of Construction and Innovative Contracting can also be consulted regarding potential alternative contracting methods.

Conclusion:

Based on the findings & conclusions above, further consideration of accelerated bridge construction is warranted:

YES         NO           Project Manager Initials: ________    Date: __________

Comments:

After thoroughly reviewing the responses to the questions, the District Project Manager, in conjunction with other appropriate experts and the Bridge Office should make a final determination regarding whether or not further consideration of ABC is warranted.

Example responses may include:

NO

“A suitable detour is available and the traffic demands at this site do not warrant the use of ABC.”

“Staging can be facilitated using ½ at-a-time construction (or other staging method) without the use of ABC.”

“Bridge construction is not on the critical path and the overall construction schedule will not benefit by using ABC.”

“Conventional bridge construction methods will adequately address the schedule and user impacts on this project.”

“The use of A+B bidding (or other contract administration alternative) will be used in lieu of ABC.”

YES

“Roadway user impacts and safety make ABC a viable alternative.”

“Use of a lateral slide (or other ABC alternative) will be further investigated.”